# Time And Manual Effort

# Project Estimation Report

Version: 1.0

Generated Date: 2026-10-12 08:21 UTC

Generated by: SDLC AI BRD/FRD Generation Agent

# Table of Contents

Update this field in Microsoft Word to refresh page numbers.

# Project Estimation Report

## 1. Overview

The project aims to streamline and automate the employee onboarding process, which is currently fragmented across various departments. The scope includes developing a centralized system that enhances the onboarding experience, ensures timely provisioning of assets and access, and provides real-time visibility into onboarding status. The estimation is based on the number of functional requirements (FRs) outlined in the Functional Requirements Document (FRD), their complexity, and the technology stack specified in the Business Requirements Document (BRD), which includes Python/FastAPI for the backend, Next.js for the frontend, and SQL for the database.

## 2. Timeline

### 2.1 Sprint Breakdown

The project will be executed in a series of sprints, each lasting two weeks. The following table outlines the sprint breakdown, focus areas, and the corresponding functional requirements:

| Sprint | Duration | Focus Area | FRs Covered |
| --- | --- | --- | --- |
| Sprint 1 | 2 weeks | Onboarding Checklist & Notifications | FR-001, FR-002 |
| Sprint 2 | 2 weeks | Document Management | FR-003 |
| Sprint 3 | 2 weeks | Status Tracking & Asset Requests | FR-004, FR-005 |
| Sprint 4 | 2 weeks | Meeting Scheduling | FR-006 |
| Sprint 5 | 2 weeks | SLA Tracking & Escalation | FR-008 |
| Sprint 6 | 2 weeks | Integrations | FR-011, FR-012, FR-013, FR-014, FR-015, FR-016, FR-017, FR-018 |
| Sprint 7 | 2 weeks | Analytics & Reporting | FR-009, FR-010 |
| **Total** | **14 weeks** | **N/A** | **All FRs** |

### 2.2 Phase Summary

**Discovery & Setup:** 1 week

**Development & Sprint Execution (7 sprints):** 14 weeks

**QA & Testing:** 2 weeks

**UAT & Deployment:** 1 week

### 2.3 Total Timeline

Estimated Project Duration: 18 weeks (90 working days across 7 sprints).

## 3. Team Structure

### 3.1 Recommended Team

The following roles are recommended based on the functional requirements outlined in the FRD:

| Role | Count | Key Responsibilities |
| --- | --- | --- |
| Senior Backend Developer | 1 | Develop backend services for onboarding checklist, notifications, and integrations. |
| Frontend Developer | 1 | Build user-facing portals, forms, and dashboards described in the FRD. |
| QA Engineer | 1 | Conduct testing for all developed features and ensure quality assurance. |
| Project Manager | 1 | Oversee project execution, manage timelines, and coordinate team activities. |
| Business Analyst | 1 | Gather requirements, facilitate communication between stakeholders, and ensure alignment with business objectives. |
| AI/ML Engineer | 1 | Design and implement AI-powered onboarding assistant for employee queries. |

### 3.2 Team Size

The total team headcount is 6. All roles are full-time, with no shared or part-time roles indicated.

## 4. Cost Estimate

### 4.1 Effort Breakdown

The following table estimates the working days for each role:

| Role | Count | Working Days | Day Rate (Offshore) | Day Rate (Onshore) |
| --- | --- | --- | --- | --- |
| Senior Backend Developer | 1 | 90 | $900-$1,200 | $1,800-$2,500 |
| Frontend Developer | 1 | 90 | $600-$900 | $1,200-$1,800 |
| QA Engineer | 1 | 90 | $400-$700 | $800-$1,200 |
| Project Manager | 1 | 90 | $500-$800 | $1,000-$1,500 |
| Business Analyst | 1 | 90 | $500-$750 | $1,000-$1,500 |
| AI/ML Engineer | 1 | 90 | $900-$1,200 | $1,800-$2,500 |

### 4.2 Total Cost Range

| Scenario | Estimated Cost (INR) |
| --- | --- |
| Offshore Team | ₹2.91 Crores (INR 29,070,000) - ₹4.25 Crores (INR 42,457,500) |
| Onshore Team | ₹5.81 Crores (INR 58,140,000) - ₹8.41 Crores (INR 84,150,000) |
| Blended (50/50) | ₹4.36 Crores (INR 43,605,000) - ₹6.33 Crores (INR 63,303,750) |

*Note: Exchange rate assumption: 1 USD = 85.00 INR.*

### 4.3 Additional Costs

Infrastructure costs are estimated based on the constraints outlined in the BRD. The following table summarizes the estimated monthly costs for relevant services:

| Service | Estimated Monthly Cost |
| --- | --- |
| Azure App Service | $50-$200 |
| Azure SQL / PostgreSQL | $100-$300 |
| Azure API Management | $100-$500 |
| Monitoring (Application Insights) | $50-$150 |

Infrastructure costs are assumed for a moderate-scale deployment. Actual costs depend on usage volume and Azure pricing tier.

## 5. Key Assumptions

The following assumptions were made during the estimation:

The team will consist of experienced professionals, leading to a standard sprint velocity.

The project will follow an Agile methodology with two-week sprints.

Integration complexity will be manageable within the defined scope.

## 6. Risks & Buffers

Potential risks include scope changes, integration complexity, and resource availability. A recommended buffer of 15-20% should be added to the base estimate to accommodate these risks.

## 7. Disclaimer

> Disclaimer: This is a rough order-of-magnitude (ROM) estimate generated by SDLC AI based on the functional requirements provided. Actual timelines and costs may vary significantly depending on team experience, technology choices, organisational processes, integration complexity, and scope changes. This estimate should not be used as a contractual basis without further detailed planning and stakeholder review.