# Organizations Spend Significant Time And

# Project Estimation Report

Version: 1.0

Generated Date: 2026-07-15 12:52 UTC

Generated by: SDLC AI BRD/FRD Generation Agent

# Table of Contents

Update this field in Microsoft Word to refresh page numbers.

# Project Estimation Report

## 1. Overview

The project aims to streamline and automate the employee onboarding process, addressing inefficiencies caused by manual coordination among HR, IT, and reporting managers. The estimation is based on the functional requirements outlined in the FRD, which includes 13 functional requirements (FRs) that vary in priority. The complexity of the project is moderate, focusing on developing a self-service employee portal, document management, and workflow automation.

## 2. Timeline

### 2.1 Sprint Breakdown

The project will be divided into six sprints, each lasting two weeks, with a focus on specific areas of development. The breakdown is as follows:

| Sprint   | Duration | Focus Area                        | FRs Covered                          |

|----------|----------|-----------------------------------|--------------------------------------|

| Sprint 1 | 2 weeks  | Employee Portal                   | FR-001, FR-002                       |

| Sprint 2 | 2 weeks  | Approval Workflows                | FR-003, FR-004                       |

| Sprint 3 | 2 weeks  | SLA Monitoring and Notifications   | FR-005, FR-006                       |

| Sprint 4 | 2 weeks  | Audit Logs and Document Repository | FR-007, FR-009                       |

| Sprint 5 | 2 weeks  | Customizable Checklists and Reporting | FR-008, FR-010                       |

| Sprint 6 | 2 weeks  | Workflow Configuration and Final Adjustments | FR-011, FR-012, FR-013              |

### 2.2 Phase Summary

The project phases are estimated as follows:

Discovery/Setup: 2 weeks

Development: 12 weeks (6 sprints)

QA & Testing: 4 weeks

UAT & Deployment: 2 weeks

### 2.3 Total Timeline

The overall estimated project duration is 20 weeks. The BRD does not specify a strict timeline constraint; therefore, this estimation is achievable without risk.

## 3. Team Structure

### 3.1 Recommended Team

The following roles are recommended based on the functional requirements:

| Role                     | Count | Key Responsibilities                                           |

|--------------------------|-------|--------------------------------------------------------------|

| Senior Backend Developer  | 1     | Develop backend services for the employee portal and workflows |

| Mid-Level Developer       | 1     | Assist in development and integration of features            |

| QA Engineer               | 1     | Conduct testing and ensure quality of the onboarding solution |

| Project Manager           | 1     | Oversee project execution and manage timelines and resources  |

| Business Analyst          | 1     | Gather requirements and ensure alignment with business needs  |

### 3.2 Team Size

The total team headcount is 5. All roles are full-time, with no shared or part-time roles.

## 4. Cost Estimate

### 4.1 Effort Breakdown

The estimated working days for each role are as follows:

| Role                     | Count | Working Days | Day Rate (Offshore) | Day Rate (Onshore) |

|--------------------------|-------|--------------|----------------------|---------------------|

| Senior Backend Developer  | 1     | 45           | $900-$1,200          | $1,800-$2,500       |

| Mid-Level Developer       | 1     | 45           | $600-$900            | $1,200-$1,800       |

| QA Engineer               | 1     | 30           | $400-$700            | $800-$1,200         |

| Project Manager           | 1     | 20           | $500-$800            | $1,000-$1,500       |

| Business Analyst          | 1     | 20           | $500-$750            | $1,000-$1,500       |

### 4.2 Total Cost Range

| Scenario        | Estimated Cost               |

|------------------|------------------------------|

| Offshore Team     | $XX,XXX - $XX,XXX            |

| Onshore Team      | $XX,XXX - $XX,XXX            |

| Blended (50/50)   | $XX,XXX - $XX,XXX            |

### 4.3 Additional Costs

The following infrastructure costs are estimated based on the constraints outlined in the BRD:

| Service                          | Estimated Monthly Cost |

|----------------------------------|------------------------|

| Azure Kubernetes Service (AKS)   | $200-$800              |

| Azure Blob Storage               | $20-$100               |

| Azure App Service                | $50-$200               |

| Azure SQL / PostgreSQL          | $100-$300              |

Infrastructure costs assumed for a moderate-scale deployment. Actual costs depend on usage volume and Azure pricing tier.

## 5. Key Assumptions

The estimation assumes a team with moderate experience, a sprint velocity of 3-4 functional requirements per sprint, and no significant scope changes during the project.

## 6. Risks & Buffers

Potential risks include scope changes, integration complexity, and resource availability. A recommended buffer of 15% has been added to the base estimate to accommodate unforeseen challenges.

## 7. Disclaimer

> Disclaimer: This is a rough order-of-magnitude (ROM) estimate generated by SDLC AI based on the functional requirements provided. Actual timelines and costs may vary significantly depending on team experience, technology choices, organisational processes, integration complexity, and scope changes. This estimate should not be used as a contractual basis without further detailed planning and stakeholder review.