# Amg Staffing And Recruitment

# Project Estimation Report

Version: 1.0

Generated Date: 2026-07-09 07:52 UTC

Generated by: SDLC AI BRD/FRD Generation Agent

# Table of Contents

Update this field in Microsoft Word to refresh page numbers.

# Project Estimation Report

## 1. Overview

The project involves developing an Interview Scheduling and Feedback Collection (ISFIS) platform for a staffing and recruitment firm. The scope includes automated interview scheduling, associate matching, client feedback collection, and dashboard reporting. The estimation basis is the provided Functional Requirement Document (FRD), which outlines 11 functional requirements. The project's complexity is moderate, and the technology stack is inferred to be a web-based application with integrations to Outlook or Gmail and Google Calendar or Outlook Calendar.

## 2. Timeline

### 2.1 Sprint Breakdown

| Sprint | Duration | Focus Area | FRs Covered |

|--------|----------|------------|-------------|

| Sprint 1 | 2 weeks | Interview Scheduling | FR-001, FR-005, FR-006 |

| Sprint 2 | 2 weeks | Associate Matching | FR-002, FR-007 |

| Sprint 3 | 2 weeks | Client Feedback Collection | FR-003, FR-008 |

| Sprint 4 | 2 weeks | Dashboard and Reporting | FR-004, FR-009 |

| Sprint 5 | 2 weeks | Integration and Testing | FR-005, FR-006, FR-010 |

### 2.2 Phase Summary

The project phases are:

Discovery/Setup: 1 week

Development: 10 weeks (5 sprints)

QA & Testing: 2 weeks

UAT & Deployment: 2 weeks

### 2.3 Total Timeline

The overall estimated project duration is 15 weeks.

## 3. Team Structure

### 3.1 Recommended Team

| Role | Count | Key Responsibilities |

|------|-------|---------------------|

| Senior Backend Developer | 1 | Implementing interview scheduling, associate matching, and client feedback collection features |

| Mid-Level Frontend Developer | 1 | Developing the dashboard and reporting features |

| QA Engineer | 1 | Testing and validating the application |

| DevOps Engineer | 1 | Ensuring infrastructure and deployment |

| Project Manager | 1 | Coordinating the project and team |

| Business Analyst | 1 | Ensuring requirements are met and providing support |

### 3.2 Team Size

The total team headcount is 6. The roles are expected to be full-time for the duration of the project.

## 4. Cost Estimate

### 4.1 Effort Breakdown

| Role | Count | Working Days | Day Rate (Offshore) | Day Rate (Onshore) |

|------|-------|-------------|--------------------|--------------------|

| Senior Backend Developer | 1 | 60 | $900-$1,200 | $1,800-$2,500 |

| Mid-Level Frontend Developer | 1 | 40 | $600-$900 | $1,200-$1,800 |

| QA Engineer | 1 | 30 | $400-$700 | $800-$1,200 |

| DevOps Engineer | 1 | 20 | $600-$900 | $1,200-$1,800 |

| Project Manager | 1 | 30 | $500-$800 | $1,000-$1,500 |

| Business Analyst | 1 | 20 | $500-$750 | $1,000-$1,500 |

### 4.2 Total Cost Range

| Scenario | Estimated Cost |

|----------|---------------|

| Offshore Team | $120,000 - $180,000 |

| Onshore Team | $240,000 - $360,000 |

| Blended (50/50) | $180,000 - $270,000 |

### 4.3 Additional Costs

Based on the BRD constraints, the estimated monthly infrastructure cost range is:

| Service | Estimated Monthly Cost |

|----------|------------------------|

| Azure App Service | $50-$200 |

| Azure SQL / PostgreSQL | $100-$300 |

| Azure API Management | $100-$500 |

| Monitoring (Application Insights) | $50-$150 |

Note: Infrastructure costs assumed for a moderate-scale deployment. Actual costs depend on usage volume and Azure pricing tier.

## 5. Key Assumptions

The estimation assumes:

The team has moderate experience with the technology stack.

The sprint velocity is average, with some buffer for unexpected tasks.

The requirements are well-defined and stable.

## 6. Risks & Buffers

The estimation risks include:

Scope changes

Integration complexity

Resource availability

A recommended buffer of 15-20% is added to the base estimate to account for these risks.

## 7. Disclaimer

Disclaimer: This is a rough order-of-magnitude (ROM) estimate generated by SDLC AI based on the functional requirements provided. Actual timelines and costs may vary significantly depending on team experience, technology choices, organisational processes, integration complexity, and scope changes. This estimate should not be used as a contractual basis without further detailed planning and stakeholder review.