# Organizations Spend Significant Time And

# Project Estimation Report

Version: 1.0

Generated Date: 2026-07-23 06:29 UTC

Generated by: SDLC AI BRD/FRD Generation Agent

# Table of Contents

Update this field in Microsoft Word to refresh page numbers.

# Project Estimation Report

## 1. Overview

The project aims to automate and streamline the onboarding process for new employees, enhancing inter-team coordination and improving the overall experience for new hires. The estimation is based on the functional requirements outlined in the FRD, which includes a total of ten functional requirements (FRs). The complexity of the project is moderate, involving the development of a candidate-facing self-service portal, automated task assignments, and various tracking and monitoring features. The solution will be deployed on Azure cloud infrastructure, adhering to GDPR compliance and role-based access control.

## 2. Timeline

### 2.1 Sprint Breakdown

The project will be executed in four sprints, each lasting two weeks. The focus areas and the corresponding FRs covered in each sprint are as follows:

| Sprint   | Duration | Focus Area                        | FRs Covered                                |

|----------|----------|-----------------------------------|--------------------------------------------|

| Sprint 1 | 2 weeks  | Candidate-Facing Portal           | FR-001, FR-002                             |

| Sprint 2 | 2 weeks  | IT Asset and Access Management    | FR-003, FR-004, FR-005                     |

| Sprint 3 | 2 weeks  | Task Assignment and Monitoring     | FR-006, FR-007, FR-008                     |

| Sprint 4 | 2 weeks  | Finalization and Review           | FR-009, FR-010                             |

### 2.2 Phase Summary

The project phases and their estimated durations are as follows:

Discovery/Setup: 1 week

Development: 8 weeks (4 sprints)

QA & Testing: 2 weeks

UAT & Deployment: 1 week

### 2.3 Total Timeline

The overall estimated project duration is 12 weeks. The BRD constraint specifies an 8-week timeline to achieve a Minimum Viable Product (MVP). Therefore, the estimated duration exceeds the constraint by 4 weeks, which poses a risk. Recommended mitigation includes reducing the scope of Phase 1 to core functionalities, deferring non-essential features to subsequent phases.

## 3. Team Structure

### 3.1 Recommended Team

The following roles are recommended based on the functional requirements outlined in the FRD:

| Role                  | Count | Key Responsibilities                                           |

|-----------------------|-------|--------------------------------------------------------------|

| Senior Backend Developer | 1     | Develop backend services for the self-service portal, task assignments, and tracking features. |

| Frontend Developer     | 1     | Build user-facing portals, forms, and dashboards as described in the FRD. |

| QA Engineer            | 1     | Conduct testing and ensure quality assurance for all developed features. |

| Project Manager        | 1     | Oversee project execution, manage timelines, and coordinate between teams. |

| Business Analyst       | 1     | Gather requirements, facilitate communication, and ensure alignment with business objectives. |

### 3.2 Team Size

The total team headcount is 5. All roles are full-time for the duration of the project.

## 4. Cost Estimate

### 4.1 Effort Breakdown

The estimated working days for each role are as follows:

| Role                  | Count | Working Days | Day Rate (Offshore) | Day Rate (Onshore) |

|-----------------------|-------|--------------|----------------------|---------------------|

| Senior Backend Developer | 1     | 45           | $900-$1,200          | $1,800-$2,500       |

| Frontend Developer     | 1     | 45           | $400-$600            | $800-$1,200         |

| QA Engineer            | 1     | 30           | $400-$700            | $800-$1,200         |

| Project Manager        | 1     | 12           | $500-$800            | $1,000-$1,500       |

| Business Analyst       | 1     | 12           | $500-$750            | $1,000-$1,500       |

### 4.2 Total Cost Range

| Scenario        | Estimated Cost             |

|------------------|---------------------------|

| Offshore Team    | $XX,XXX - $XX,XXX         |

| Onshore Team     | $XX,XXX - $XX,XXX         |

| Blended (50/50)  | $XX,XXX - $XX,XXX         |

### 4.3 Additional Costs

The estimated monthly infrastructure costs based on the services required for the project are as follows:

| Service                          | Estimated Monthly Cost |

|----------------------------------|------------------------|

| Azure App Service                | $50-$200               |

| Azure SQL / PostgreSQL           | $100-$300              |

| Azure Blob Storage               | $20-$100               |

| Monitoring (Application Insights) | $50-$150               |

Infrastructure costs are assumed for a moderate-scale deployment. Actual costs depend on usage volume and Azure pricing tier.

## 5. Key Assumptions

The following assumptions were made during the estimation:

The team will have the necessary experience and skills to execute the project efficiently.

The sprint velocity is assumed to be consistent throughout the project.

No significant scope changes will occur during the project execution.

## 6. Risks & Buffers

The primary risks associated with this estimation include potential scope changes, integration complexity, and resource availability. A recommended buffer of 15-20% should be added to the base estimate to accommodate unforeseen challenges.

## 7. Disclaimer

> Disclaimer: This is a rough order-of-magnitude (ROM) estimate generated by SDLC AI based on the functional requirements provided. Actual timelines and costs may vary significantly depending on team experience, technology choices, organisational processes, integration complexity, and scope changes. This estimate should not be used as a contractual basis without further detailed planning and stakeholder review.