# Building Automated Customer Onboarding

# Project Estimation Report

Version: 1.0

Generated Date: 2026-10-08 10:54 UTC

Generated by: SDLC AI BRD/FRD Generation Agent

# Table of Contents

Update this field in Microsoft Word to refresh page numbers.

# Project Estimation Report

## 1. Overview

The project aims to automate the customer onboarding process for business customers, reducing the onboarding time from 7 days to under 15 minutes. The scope includes implementing various functional requirements (FRs) such as digital identity verification, automated document extraction, real-time KYC/AML checks, and workflow automation. The estimation is based on the number of FRs identified in the Functional Requirements Document (FRD), their complexity, and the technology stack specified, including FastAPI for backend services, Next.js for frontend development, and SQL for database management.

## 2. Timeline

### 2.1 Sprint Breakdown

| Sprint | Duration | Focus Area | FRs Covered |
| --- | --- | --- | --- |
| Sprint 1 | 2 weeks | Phase 1 Implementation | FR-001 to FR-003 |
| Sprint 2 | 2 weeks | Phase 2 Implementation | FR-004 to FR-006 |
| Sprint 3 | 2 weeks | Phase 3 Implementation | FR-007 to FR-009 |
| Sprint 4 | 2 weeks | Phase 4 Implementation | FR-010 to FR-012 |
| Sprint 5 | 2 weeks | Phase 5 Implementation | FR-013 to FR-015 |
| Sprint 6 | 2 weeks | Phase 6 Implementation | FR-016 to FR-018 |

### 2.2 Phase Summary

**Discovery & Setup:** 1 week

**Development & Sprint Execution (6 sprints):** 12 weeks

**QA & Testing:** 2 weeks

**UAT & Deployment:** 1 week

### 2.3 Total Timeline

Estimated Project Duration: 16 weeks (80 working days across 6 sprints).

## 3. Team Structure

### 3.1 Recommended Team

| Role | Count | Key Responsibilities |
| --- | --- | --- |
| Senior Backend Developer | 1 | Develop backend services using FastAPI, implement database management with SQL, ensure compliance with KYC, AML, GDPR, and SOC2 regulations. |
| Frontend Developer | 1 | Build user-facing portals, forms, and dashboards as described in the FRD. |
| QA Engineer | 1 | Conduct testing for all developed features, ensure quality and compliance with defined SLAs. |
| Project Manager | 1 | Oversee project execution, manage timelines, and coordinate between teams. |
| Business Analyst | 1 | Gather requirements, ensure alignment with business objectives, and validate project outcomes. |
| AI/ML Engineer | 1 | Design and implement AI matching model, NLP summarization pipeline, skill gap detection. |

### 3.2 Team Size

The total team headcount is 6. All roles are full-time, with no shared or part-time roles indicated.

## 4. Cost Estimate

### 4.1 Effort Breakdown

| Role | Count | Working Days | Day Rate (Offshore) | Day Rate (Onshore) |
| --- | --- | --- | --- | --- |
| Senior Backend Developer | 1 | 80 | $900-$1,200 | $1,800-$2,500 |
| Frontend Developer | 1 | 80 | $600-$900 | $1,200-$1,800 |
| QA Engineer | 1 | 80 | $400-$700 | $800-$1,200 |
| Project Manager | 1 | 80 | $500-$800 | $1,000-$1,500 |
| Business Analyst | 1 | 80 | $500-$750 | $1,000-$1,500 |
| AI/ML Engineer | 1 | 80 | $900-$1,200 | $1,800-$2,500 |

### 4.2 Total Cost Range

| Scenario | Estimated Cost (INR) |
| --- | --- |
| Offshore Team | ₹2.58 Crores (INR 25,840,000) - ₹3.77 Crores (INR 37,740,000) |
| Onshore Team | ₹5.17 Crores (INR 51,680,000) - ₹7.48 Crores (INR 74,800,000) |
| Blended (50/50) | ₹3.88 Crores (INR 38,760,000) - ₹5.63 Crores (INR 56,270,000) |

*Note: Exchange rate assumption: 1 USD = 85.00 INR.*

### 4.3 Additional Costs

| Service | Estimated Monthly Cost |
| --- | --- |
| Azure Kubernetes Service (AKS) | $200-$800 |
| Azure Blob Storage | $20-$100 |
| Azure App Service | $50-$200 |
| Azure SQL | $100-$300 |
| Monitoring (Application Insights) | $50-$150 |

Infrastructure costs assumed for a moderate-scale deployment. Actual costs depend on usage volume and Azure pricing tier.

## 5. Key Assumptions

The team will consist of experienced professionals familiar with the specified technology stack.

The project will follow a standard sprint velocity of 2 weeks per sprint.

No significant scope changes will occur during the project lifecycle.

## 6. Risks & Buffers

Potential risks include scope changes, integration complexity, and resource availability. A recommended buffer of 15-20% should be added to the base estimate to accommodate unforeseen challenges.

## 7. Disclaimer

> Disclaimer: This is a rough order-of-magnitude (ROM) estimate generated by SDLC AI based on the functional requirements provided. Actual timelines and costs may vary significantly depending on team experience, technology choices, organisational processes, integration complexity, and scope changes. This estimate should not be used as a contractual basis without further detailed planning and stakeholder review.