# Spend Significant Time And

# Project Estimation Report

Version: 1.0

Generated Date: 2026-10-08 10:43 UTC

Generated by: SDLC AI BRD/FRD Generation Agent

# Table of Contents

Update this field in Microsoft Word to refresh page numbers.

# Project Estimation Report

## 1. Overview

The project aims to streamline and automate the employee onboarding process, which is currently fragmented across various departments. The scope includes the development of a centralized onboarding system that enhances candidate experience, ensures timely provisioning of assets and access, and provides real-time visibility into onboarding status. The estimation is based on the number of functional requirements (FRs) identified in the Functional Requirements Document (FRD), their complexity, and the technologies inferred from the Business Requirements Document (BRD), including FastAPI, Next.js, and SQL.

## 2. Timeline

### 2.1 Sprint Breakdown

The project will be executed in a series of sprints, each lasting two weeks. The following table outlines the sprint breakdown with focus areas and covered FRs:

| Sprint | Duration | Focus Area | FRs Covered |
| --- | --- | --- | --- |
| Sprint 1 | 2 weeks | Onboarding Checklist & Notifications | FR-001, FR-002 |
| Sprint 2 | 2 weeks | Document Management | FR-003 |
| Sprint 3 | 2 weeks | Status Tracking & Task Automation | FR-004, FR-005, FR-008 |
| Sprint 4 | 2 weeks | Meeting Scheduling | FR-006, FR-012, FR-013 |
| Sprint 5 | 2 weeks | Integrations | FR-011, FR-014, FR-015, FR-016, FR-017, FR-018 |
| Sprint 6 | 2 weeks | Analytics & Reporting | FR-009, FR-010 |
| **Total** | **12 weeks** |  |  |

### 2.2 Phase Summary

**Discovery & Setup:** 1 week

**Development & Sprint Execution (6 sprints):** 12 weeks

**QA & Testing:** 2 weeks

**UAT & Deployment:** 1 week

### 2.3 Total Timeline

Estimated Project Duration: 16 weeks (80 working days across 6 sprints).

## 3. Team Structure

### 3.1 Recommended Team

The following roles are recommended based on the functional requirements in the FRD:

| Role | Count | Key Responsibilities |
| --- | --- | --- |
| Senior Backend Developer | 1 | Develop backend services for onboarding checklist, task assignment, and integrations. |
| Frontend Developer | 1 | Build user-facing portals, forms, and dashboards described in the FRD. |
| QA Engineer | 1 | Conduct testing for all developed features and ensure quality assurance. |
| Project Manager | 1 | Oversee project execution, manage timelines, and coordinate between teams. |
| Business Analyst | 1 | Gather requirements, facilitate communication, and ensure alignment with business goals. |
| AI/ML Engineer | 1 | Design and implement AI-powered onboarding assistant for employee queries. |

### 3.2 Team Size

The total team headcount is 6. All roles are full-time, with no shared or part-time roles indicated.

## 4. Cost Estimate

### 4.1 Effort Breakdown

The following table outlines the estimated working days for each role:

| Role | Count | Working Days | Day Rate (Offshore) | Day Rate (Onshore) |
| --- | --- | --- | --- | --- |
| Senior Backend Developer | 1 | 80 | $900-$1,200 | $1,800-$2,500 |
| Frontend Developer | 1 | 80 | $400-$600 | $800-$1,200 |
| QA Engineer | 1 | 80 | $400-$700 | $800-$1,200 |
| Project Manager | 1 | 80 | $500-$800 | $1,000-$1,500 |
| Business Analyst | 1 | 80 | $500-$750 | $1,000-$1,500 |
| AI/ML Engineer | 1 | 80 | $900-$1,200 | $1,800-$2,500 |

### 4.2 Total Cost Range

| Scenario | Estimated Cost (INR) |
| --- | --- |
| Offshore Team | ₹2.45 Crores (INR 24,480,000) - ₹3.57 Crores (INR 35,700,000) |
| Onshore Team | ₹4.90 Crores (INR 48,960,000) - ₹7.07 Crores (INR 70,720,000) |
| Blended (50/50) | ₹3.67 Crores (INR 36,720,000) - ₹5.32 Crores (INR 53,210,000) |

*Note: Exchange rate assumption: 1 USD = 85.00 INR.*

### 4.3 Additional Costs

Based on the constraints outlined in the BRD, the estimated monthly infrastructure costs are as follows:

| Service | Estimated Monthly Cost |
| --- | --- |
| Azure Kubernetes Service (AKS) | $200-$800 |
| Azure Blob Storage | $20-$100 |
| Azure SQL / PostgreSQL | $100-$300 |
| Azure App Service | $50-$200 |
| Monitoring (Application Insights) | $50-$150 |

Infrastructure costs are assumed for a moderate-scale deployment. Actual costs depend on usage volume and Azure pricing tier.

## 5. Key Assumptions

The estimation assumes a team with moderate experience, a sprint velocity of 2 weeks per sprint, and that all functional requirements will be implemented as specified without significant scope changes.

## 6. Risks & Buffers

Key risks include potential scope changes, integration complexity, and resource availability. A recommended buffer of 15-20% should be added to the base estimate to accommodate these risks.

## 7. Disclaimer

> Disclaimer: This is a rough order-of-magnitude (ROM) estimate generated by SDLC AI based on the functional requirements provided. Actual timelines and costs may vary significantly depending on team experience, technology choices, organisational processes, integration complexity, and scope changes. This estimate should not be used as a contractual basis without further detailed planning and stakeholder review.