# Amg Staffing And

# Project Estimation Report

Version: 1.0

Generated Date: 2026-07-23 04:51 UTC

Generated by: SDLC AI BRD/FRD Generation Agent

# Table of Contents

Update this field in Microsoft Word to refresh page numbers.

# Project Estimation Report

## 1. Overview

The project aims to digitize and automate the end-to-end interview lifecycle, addressing inefficiencies caused by manual processes. The scope includes the development of features for automated interview scheduling, reminder notifications, associate matching to job descriptions, tracking interview outcomes, post-interview response forms, client feedback collection, and automated feedback reminders. The estimation is based on the number of functional requirements (FRs) outlined in the FRD, their complexity, and the technology inferred from the BRD, particularly focusing on cloud deployment on Azure.

## 2. Timeline

### 2.1 Sprint Breakdown

The project will be divided into five sprints, each lasting two weeks, with a focus on delivering specific functional requirements:

| Sprint   | Duration | Focus Area                      | FRs Covered                          |

|----------|----------|---------------------------------|--------------------------------------|

| Sprint 1 | 2 weeks  | Interview Scheduling             | FR-001, FR-002                       |

| Sprint 2 | 2 weeks  | Associate Matching               | FR-003                               |

| Sprint 3 | 2 weeks  | Interview Outcome Tracking       | FR-004                               |

| Sprint 4 | 2 weeks  | Post-Interview Forms & Feedback  | FR-005, FR-006, FR-007               |

| Sprint 5 | 2 weeks  | Feedback Analysis                | FR-008, FR-009                       |

### 2.2 Phase Summary

The project phases are as follows:

Discovery/Setup: 2 weeks

Development: 10 weeks (5 sprints)

QA & Testing: 2 weeks

UAT & Deployment: 2 weeks

### 2.3 Total Timeline

The overall estimated project duration is 16 weeks. The BRD specifies a 10-week timeline to MVP, indicating that the estimated duration exceeds this constraint. This presents a risk. Recommended mitigation includes reducing the scope to core scheduling and feedback features only, deferring advanced matching and analysis capabilities to a subsequent phase.

## 3. Team Structure

### 3.1 Recommended Team

The following roles are recommended based on the functional requirements outlined in the FRD:

| Role                     | Count | Key Responsibilities                                           |

|--------------------------|-------|--------------------------------------------------------------|

| Senior Backend Developer  | 1     | Develop and implement automated scheduling and matching features. |

| QA Engineer               | 1     | Conduct testing for all developed features and ensure quality. |

| Project Manager           | 1     | Oversee project execution, manage timelines, and coordinate teams. |

| Business Analyst          | 1     | Gather requirements, facilitate communication between stakeholders. |

### 3.2 Team Size

The total team headcount is 4. All roles are full-time and dedicated to the project.

## 4. Cost Estimate

### 4.1 Effort Breakdown

The estimated working days for each role are as follows:

| Role                     | Count | Working Days | Day Rate (Offshore) | Day Rate (Onshore) |

|--------------------------|-------|--------------|---------------------|---------------------|

| Senior Backend Developer  | 1     | 45           | $900-$1,200         | $1,800-$2,500       |

| QA Engineer               | 1     | 20           | $400-$700           | $800-$1,200         |

| Project Manager           | 1     | 16           | $500-$800           | $1,000-$1,500       |

| Business Analyst          | 1     | 10           | $500-$750           | $1,000-$1,500       |

### 4.2 Total Cost Range

| Scenario         | Estimated Cost        |

|------------------|-----------------------|

| Offshore Team     | $36,000 - $54,000     |

| Onshore Team      | $80,800 - $120,800    |

| Blended (50/50)   | $58,400 - $87,400     |

### 4.3 Additional Costs

Based on the BRD constraints, the estimated monthly infrastructure costs are as follows:

| Service                          | Estimated Monthly Cost |

|----------------------------------|------------------------|

| Azure App Service                 | $50-$200               |

| Azure SQL / PostgreSQL            | $100-$300              |

| Monitoring (Application Insights) | $50-$150               |

Infrastructure costs are assumed for a moderate-scale deployment. Actual costs depend on usage volume and Azure pricing tier.

## 5. Key Assumptions

The estimation assumes a team with moderate experience levels, a sprint velocity of 3-4 functional requirements completed per sprint, and no significant scope changes during the project.

## 6. Risks & Buffers

Key risks include potential scope changes, integration complexities, and resource availability. A recommended buffer of 15-20% should be added to the base estimate to accommodate these risks.

## 7. Disclaimer

> Disclaimer: This is a rough order-of-magnitude (ROM) estimate generated by SDLC AI based on the functional requirements provided. Actual timelines and costs may vary significantly depending on team experience, technology choices, organisational processes, integration complexity, and scope changes. This estimate should not be used as a contractual basis without further detailed planning and stakeholder review.