# Organizations spend significant time and manual effort onboarding

# Estimation

Version: 1.0

Generated Date: 2026-07-08 07:03 UTC

Generated by: SDLC AI BRD/FRD Generation Agent

# Table of Contents

Update this field in Microsoft Word to refresh page numbers.

# Traceability Summary

| BRD Item | FRD Requirement |
| --- | --- |
| TBD | TBD |

# Project Estimation Report

## 1. Overview

The project aims to develop an onboarding platform that streamlines the onboarding process for new employees, reducing manual coordination efforts and improving the overall candidate experience. The scope of the project includes creating onboarding requests, uploading and verifying documents, assigning tasks automatically, configuring approval workflows, tracking onboarding progress, implementing role-based access control, and generating onboarding reports. The estimation basis is the provided Functional Requirement Document (FRD), which outlines 7 key functional requirements. The technology stack and complexity are inferred from the FRD, assuming a standard web-based application with a backend database and user interface.

## 2. Timeline

### 2.1 Sprint Breakdown

| Sprint | Duration | Focus Area | FRs Covered |

|--------|----------|------------|-------------|

| Sprint 1 | 2 weeks | Onboarding Request Creation | FR-001 |

| Sprint 2 | 2 weeks | Document Upload and Verification | FR-002 |

| Sprint 3 | 2 weeks | Automated Task Assignment and Approval Workflows | FR-003, FR-004 |

| Sprint 4 | 2 weeks | Onboarding Progress Tracking and Role-Based Access Control | FR-005, FR-006 |

| Sprint 5 | 2 weeks | Onboarding Reporting and Finalize | FR-007 |

### 2.2 Phase Summary

The project can be broken down into the following phases:

Discovery/Setup: 2 weeks

Development: 10 weeks (5 sprints)

QA & Testing: 4 weeks

UAT & Deployment: 4 weeks

### 2.3 Total Timeline

The overall estimated project duration is 20 weeks.

## 3. Team Structure

### 3.1 Recommended Team

| Role | Count | Key Responsibilities |

|------|-------|---------------------|

| Senior Backend Developer | 1 | Developing backend APIs for onboarding request creation, document upload, and task assignment |

| Mid-Level Frontend Developer | 1 | Developing user interface for onboarding request creation, document upload, and onboarding progress tracking |

| QA Engineer | 1 | Testing and validating the onboarding platform |

| DevOps Engineer | 1 | Setting up and maintaining the development environment, deploying the application |

| Project Manager | 1 | Coordinating the project, managing timelines, and ensuring deliverables |

| Business Analyst | 1 | Reviewing and refining the functional requirements, ensuring they meet the business needs |

### 3.2 Team Size

The total team headcount is 6. The Project Manager and Business Analyst roles may be part-time or shared with other projects.

## 4. Cost Estimate

### 4.1 Effort Breakdown

| Role | Count | Working Days | Day Rate (Offshore) | Day Rate (Onshore) |

|------|-------|-------------|--------------------|--------------------|

| Senior Backend Developer | 1 | 60 | $900-$1,200 | $1,800-$2,500 |

| Mid-Level Frontend Developer | 1 | 50 | $600-$900 | $1,200-$1,800 |

| QA Engineer | 1 | 40 | $400-$700 | $800-$1,200 |

| DevOps Engineer | 1 | 30 | $600-$900 | $1,200-$1,800 |

| Project Manager | 1 | 20 | $500-$800 | $1,000-$1,500 |

| Business Analyst | 1 | 15 | $500-$750 | $1,000-$1,500 |

### 4.2 Total Cost Range

| Scenario | Estimated Cost |

|----------|---------------|

| Offshore Team | $120,000 - $180,000 |

| Onshore Team | $240,000 - $360,000 |

| Blended (50/50) | $180,000 - $270,000 |

### 4.3 Additional Costs

TBD - to be estimated during project planning.

## 5. Key Assumptions

The estimation assumes that the team members have average to above-average experience, the technology stack is relatively standard, and the project scope does not change significantly during development.

## 6. Risks & Buffers

The estimation risks include scope changes, integration complexity, and resource availability. A recommended buffer of 15-20% should be added to the base estimate to account for these risks.

## 7. Disclaimer

Disclaimer: This is a rough order-of-magnitude (ROM) estimate generated by SDLC AI based on the functional requirements provided. Actual timelines and costs may vary significantly depending on team experience, technology choices, organisational processes, integration complexity, and scope changes. This estimate should not be used as a contractual basis without further detailed planning and stakeholder review.